## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | University Analytical Study of Planned Obsolescence
Total Amount Requested from SSC: | 42630 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 09/26/2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Designing a data base | 20 |  | 2024-02-26
Registering stakeholders | 4 |  | 2024-03-26
Scheduling interviews and generating interview algorithms | 4 |  | 2024-04-26
Engineering a scale system for planned obsolescence | 8 |  | 2024-06-20
Creating a Tableau dashboard to display findings | 8 |  | 2024-08-20
Hire an outside consultant to provide counter-metrics comparison | 12 |  | 2024-11-20
Present results to board of trustees | 4 |  | 2024-12-20
Publish Abstract and results in Sustainability Now | 16 |  | 2025-04-20
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Computer and presentation materials | 2500 | 1 | 2500
Interviewing Material | 1000 | 1 | 1000
0
0
0
0
0
0
0
0
|  | Subtotal | 3500
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Hiring publication company and editors | 7500 | 1 | 7500
Student Interns | 15.5 | 1660 | 25730
Supply Chain Metric consultant | 4500 | 1 | 4500
0
0
0
0
0
0
0
|  | Subtotal | 37730
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Tableau yearly subscription | 700 | 2 | 1400
0
0
0
0
0
0
0
0
0
|  | Subtotal | 1400
|  | TOTAL BUDGET | 42630
End of Application